## Task Checklist
| Tasks: | Details: | Date Completed | "Phase" | Category | Task Assigned To: | Step Number
FALSE | Make a Google Drive Folder '(Location)_(Year)' | Put this folder in Google Drive in the 'Rally' > '(Rally Year)' |  | 1 | Start |  | 1
FALSE | Make a copy of blank budget form & Checklist, and copy into Rally folders | Blank budget form & checklist can be found in folders'Departments' > 'Rally' > ' - Blank Forms'. Right click blank budget form to make a copy. Rename copy, and move to new '(Location)_(Year)' folder |  | 1 | Start |  | 2
FALSE | Set Initial Meeting with Pastors | Work with Ex. Director and pastor point person to set a meeting date to invite other pastors to. |  | 1 | Start |  | 3
FALSE | Gather Pastor/ Church Emails | Using past event budget forms to get emails, and working with the Ex. Director, get these emails for pastors/ leaders in a specific area. Track names, emails, and participation in the relevant Budget Form, 'Church Partnership' tab. |  | 1 | Start |  | 4
FALSE | Email invitation to each church | Copy emails from budget sheet, on the 'Church Partnership' tab. |  | 1 | Start |  | 5
FALSE | Order food for Pastor meeting | IF it is decided to get food for the meeting. If not, mark as complete anyway. |  | 1 | Start |  | 6
FALSE | Send meeting reminder to pastors | Usually it's best to send an email reminder a couple days in advanced to the pastrs before the meeting. Brief and to the point, so they don't ignore it. |  | 1 | Start |  | 7
FALSE | Meet with Pastors | Pickup food, bring computer for notes, to look up info, etc. |  | 1 | Start |  | 8
FALSE | Set preliminary Date for Event | Based on Pastors meeting. Is this flexible if the venue isn't availible, or not? |  | 1 | Start |  | 9
FALSE | Set preliminary Venue for Event | Based on pastors meeting. |  | 1 | Venue |  | 10
FALSE | Get quotes for audio/ Visual | Kevin Irwin (ksisound@msn.com or 937-545-5251) with KSI Sound has been our recent go to. |  | 1 | AV |  | 11
FALSE | Get quote for photography the night of the Rally | Justin Spivey (jspiveyphoto@gmail.com) with J Spivey Photography is usually our go to. |  | 1 | Photo |  | 12
FALSE | Get quote for Venue | This usually can be done ahead of the meeting, since a lot of venue prices are set and can be found online, or with a quick email. Knowing this ahead of the pastors meeting can be a huge jumpstart in planning. |  | 1 | Venue |  | 13
FALSE | Get quote for Videography (Promo/ Highlight videos) | Jason Elam with Agape (jason@agapemedia.com) is usually our go to. It's best to know ahead of time, what all video work we might want him to do. Just a Promo? or a Highlight video too? When he knows everything ahead of time, he may give discounts for more work. |  | 1 | Video |  | 14
FALSE | Email Commitment Form to pastors/ leaders | Let the leaders know the ideal budget needed commited. Have them go to www.declare.org/commitmentform to fill out their church's commitment. Set a date (a week or two is normal) to have them back by. |  | 1 | Budget |  | 15
FALSE | Finalize the Budget with quotes on minimum and ideal budget | Work with Ex. Director to set a bare minimum budget for event, and an ideal budget. This helps get an idea of what commintments to ask for. |  | 2 | Budget |  | 16
FALSE | Create a general/ blank Planning Center plan | On PCO, create a new "plan" titled and dated with this Rally Event. Add a generic schedule based on past PCO plans and vision of this event. It can be as generic an 2 songs, 1 speaking part, 2 songs, 1 speaking part, and so on until the service is about an hour and a half. The point in this is to be able to quickly rename, move, and edit those blocks in the meeting while making the official plan. |  | 2 | Service |  | 17
FALSE | Confirm Live Stream license with CCLI | Rechout to Business Admin, who oversees the CCLI account, to confirm updated livestream abilities. Through the pandemic, it seems the details of what we are/ aren't allowed to do as far as live streaming the event have changed. |  | 2 | Livestream |  | 18
FALSE | Sign contract for audio/ visual | Contract saved in Google Drive folder |  | 2 | AV |  | 19
FALSE | Set a meeting with potential band leader(s) | Work with Ex. Director to identify potential band leader(s), and reach out to them to set a meeting. |  | 2 | Band |  | 20
FALSE | Meet with potential band leader to talk through band needs | Explain specific needs for the band leader (contacting band members, editing planning center online songs and team members, scheduling and running rehearsals, running "point" on communication with the band), and set a date to get an answer. |  | 2 | Band |  | 21
FALSE | Confirm band leader | If they say no, uncheck last step. If they say yes, pass "go" and collect $200. |  | 2 | Band |  | 22
FALSE | Coordinate with band leader who will contact other band members | Possibly in another meeting, work through possible band members with band leader(s) and ex. director, and coordinate who will contact each musician. |  | 2 | Band |  | 23
FALSE | Identify potential Choir Director | Work with Ex. Director to identify potential Choir leader, and reach out to them to set a meeting. |  | 2 | Choir |  | 24
FALSE | Meet with potential Choir Director | Meet with them and set a date to confirm they will do it. |  | 2 | Choir |  | 25
FALSE | Confirm Choir Director | If they say no, uncheck last step. If they say yes, pass "go" and collect $200. |  | 2 | Choir |  | 26
FALSE | Schedule filming with Videographers and leaders | Ask video company availibility to shoot a promo video. Select date, and email all necessary leaders if and how you need them for the promo video. |  | 2 | Video |  | 27
FALSE | Add all band members to Planning Center | This can be done by Declare or a band leader. Sometimes its easier for the band leaders to add people, than tell you everyone to add and all their information. Usually we just play a supporting role in this by checking in on the progress and asking if/how we can assist. |  | 2 | Band |  | 28
FALSE | Ensure band rehearsal dates are set | The band leader will be in charge of communicating with band, and scheduling these rehearsals. Just be sure they are shceduled and will be enough to prepare the band. |  | 2 | Band |  | 29
FALSE | Make Choir plan and rehearsal schedule | Possibly in another meeting with choir director and ex. director, set rehearsals, and cooirdinate who will be contacted to be involved, or if it will be opened up to social media and emails. |  | 2 | Choir |  | 30
FALSE | Make social media post and sned an email about joining choir | Work with Communication Cordinator to make a graphic/ posting inviting people to the choir rehearsal if they want to join it. |  | 2 | Choir |  | 31
FALSE | Submit food truck request | Go to https://www.daytonfoodtruckassociation.com/ and submit a food truck request. Food Trucks will email you back and let you know if they can or ask questions. |  | 2 | Food Trucks |  | 32
FALSE | Find out what documentation is needed for venue from the food trucks | Ask venue contact what (if any) required documentation they need from the food trucks. |  | 2 | Food Trucks |  | 33
FALSE | Request required documentation from food trucks | A.S.A.P. as possible, email the food trucks that said they will be at the event, and ask them for all of the necesary documentation. Food truck documentation has caused us some issues in the past. Food truck owners aren't always the quickest to get documents I, or reply to emails. Also, they have been known to "ghost" you, so the sooner you can get these locked down, the better! |  | 2 | Food Trucks |  | 34
FALSE | Set date and email pastors about a service order meeting | Email pastirs, inviting them to be a part of the service order planning. This isn't as necessary for all of the pastors to be at, since the more voices there are, the less productive it can be. So either invite a few key pastors (that have shown a commitment and devotion to church unity) or tell all the pastors that it isn't necessary for them to be at, but that they are invited to be a part of it still. |  | 2 | Service |  | 35
FALSE | Get quote for inflatables from rental company | No known companies we work specifically with. |  | 2 | Inflatables |  | 36
FALSE | Book photographer | Find out when they need paid by. |  | 2 | Photo |  | 37
FALSE | Create Graphics for Rally Event | Work with Communications Coordinator to have a promotional graphic(s) made. Often times, we'll make a social media graphic, that can also be used as a slide for churches to put up on sundays. |  | 2 | Promo |  | 38
FALSE | Meet about service order, and adjust plan accordingly | Adjust the generic PCO plan including service elements the pastors talk about. Sometimes its easier to take notes and adjust the plan after the meeting, because a lot of rabbit holes happen in conversation. |  | 2 | Service |  | 39
FALSE | Sign rental agreement for venue | Go through rental contract and ensure we're aware of all responsibilities we have (trash, cleanup, how much time we have, etc) with Ex. Director and sign. Save a signed copy on google drive. |  | 2 | Venue |  | 40
FALSE | Get Cert. of Insurance required by Venue | Email Mark and ask him to get certificate of insurance from our insuarnce company. Be sure it includes any necessary wording/ language the venue or other partners may require (this is often found in the contract). |  | 2 | Venue |  | 41
FALSE | Get power and access information from Venue for audio/visual and trucks | Ask venue about access for all elements of the event so we know how to communicate with A/V, Food Trucks, band, etc. |  | 2 | Venue |  | 42
FALSE | Write script for promo video | Communicate plan for promo with video company, but work with Ex. Director to write a script. |  | 2 | Video |  | 43
FALSE | Film Promo | Bring copies of script (including one for video company), and any other necessary information to pass along to leaders during filming. |  | 2 | Video |  | 44
FALSE | Confirm that songlist it finalized | Reach out to band leader and confirm that songs and arangemnts are finalized. |  | 3 | Band |  | 45
FALSE | Order food for band during day of run throughs | Make a food plan with Ex. Director on where to get it, and order a week ahead of time. |  | 3 | Food |  | 46
FALSE | Submit documentation for the food trucks to venue | Check is there is a specific date the documentation needs to be submitted by. If so, be sure to plan accordingly when setting deadlines for food trucks. |  | 3 | Food Trucks |  | 47
FALSE | Submit deposit/ contract for inflatables | Look through contract to ensure we have everything we need, and submit all neede paperwork and deposit. |  | 3 | Inflatables |  | 48
FALSE | Create ProPresenter playlist | Work with Band Leader(s) to get arrangement & song info. |  | 3 | PP |  | 49
FALSE | Send audio/ visual deposit | Check with company for due dates/ how to send deposit |  | 3 | AV |  | 50
FALSE | Confirm visual dimensions with Audio/ Visual company | Reach out to A/V company or venue and get the visual dimensions to input in ProPresenter to make sure the slides are formated correctly |  | 3 | PP |  | 51
FALSE | Import Songs to ProPresenter | In ProPresenter, you can import song lyrics using the CCLI#. In PP6, on the top bar, click "View." Scroll down, and click "Song Select." This will lead into a login process for CCLI Song Select (Refer to Ex. Director for login info). Once logged in, you can search and import songs by Title or CCLI# (CCLI# is recommended). |  | 3 | PP |  | 52
FALSE | Have slide created for partnering churches | Connect with Communications Coordinator to give them logos to put on a slide(s) |  | 3 | PP |  | 53
FALSE | Have slide created for partnering organizations | Connect with Communications Coordinator to give them logos to put on a slide(s) |  | 3 | PP |  | 54
FALSE | Have "Title Slide" created for event | Connect with Communications Coordinator to have them create this graphic/ slide |  | 3 | PP |  | 55
FALSE | Have Declare social media slide created/ imported | Connect with Communications Coordinator to create a social media slide |  | 3 | PP |  | 56
FALSE | Have any additional announcement slides created | Are there additional messages/ announcements that need share as a slide? |  | 3 | PP |  | 57
FALSE | Create slides for each "speaker" that comes up | Make a general, easy to read slide for each person that has a speaking part during the service, saying their name and affiliation for the audience. |  | 3 | PP |  | 58
FALSE | Put the sponsor slides, title slide, social media slide, and other announcement slides on a loop. | Create this looping slideshow for before the service starts, and when it ends. You can adjust this loop by clicking the timer button on the set (10 seconds usually is good). |  | 3 | PP |  | 59
FALSE | Put all slides and songs in order, ready for the night | Including speaker names, songs, graphics, annoucements, videos, etc. make sure the entire service is put in order. It seems the night never goes exactly according to plan, but its best to have everything ready so all the needs to be done during the service is advance the slides. |  | 3 | PP |  | 60
FALSE | Reach out to potential Prayer Team leader(s) | Work with Ex. Director to identify potential prayer leaders, and contact them about doing it. |  | 3 | Prayer Team |  | 61
FALSE | Confirm Prayer Team leader(s) | If they say no, work with Ex. Director to identify other possibilities |  | 3 | Prayer Team |  | 62
FALSE | Set plan for prayer team with leader(s) | Possibly in a meeting, work with prayer leader and ex. director to make a plan for who will make up the prayer team, and who/ how thye will be invited |  | 3 | Prayer Team |  | 63
FALSE | Coordinate with Executive Director a plan/ person to operate livestream | Often times, it will be a team member who runs the facebook live for an event. This should just be confirmed ahead off time. Be sure whoever is doing it has access to the facebook page to livestream, as well as a tripod/ stabilizer, and backup battery pack (we don't have one of these, but it may be good to have) |  | 3 | Livestream |  | 64
FALSE | Share promo video with pastors/ leaders | Email links to all of the promotional material to the pastors, so they can advertise at their churches. |  | 3 | Promo |  | 65
FALSE | Post promo video to YouTube | Work with Communications Coordinator to make sure this is posted. |  | 3 | Promo |  | 66
FALSE | Post promo video to Facebook | Work with Communications Coordinator to make sure this is posted. |  | 3 | Promo |  | 67
FALSE | Post promo video to Instagram | Work with Communications Coordinator to make sure this is posted. |  | 3 | Promo |  | 68
FALSE | Email promo video to email list | Work with Communications Coordinator to make sure this is emailed. |  | 3 | Promo |  | 69
FALSE | Email promo graphic to email list | Work with Communications Coordinator to make sure this is emailed. |  | 3 | Promo |  | 70
FALSE | Reach out to each "speaker" to confirm their availability | Indiviually email, text, or message each person that is hoped to be a speaker during the service. Set a date for them t get back with you in case they are unable to, you still can have time to find a replacement. |  | 3 | Service |  | 71
FALSE | Submit all required documentation to venue | Check with venue for due dates. Make sure all submitted documents are scaned and saved on google drive in the specific Rally folder. |  | 3 | Venue |  | 72
FALSE | Send venue deposit (if required) | Check with venue for due dates/ how to send deposit |  | 3 | Venue |  | 73
FALSE | Ensure all deposits and forms are submitted to all vendors | Look through contracts in google drive, to be sure you have everything you need, and that it's all been submitted (or ready to be given night of). |  | 4 | Budget |  | 74
FALSE | Email pastors who have made commitments, but still need it sent in. | Work with Ex. Director and Business Admin. to see what commitments have come in, and what still needs to be submitted. |  | 4 | Budget |  | 75
FALSE | Pickup food for band | either plan to pick this up day of, or deligate someone else to pick it up. |  | 4 | Food |  | 76
FALSE | Email pastors a final update and set a time to gather before the concert | In a breif reminder email, the week before the event, send any last minute updates out to pastors and tell them a place and time to meet before the concert starts, to go through the schedule and pray. |  | 4 | Service |  | 77
FALSE | Find Declare team/ board member to operate the Declare table | Work with Ex. Director to designate a Declare representative to operate the Declare table (sign up forms, Declare info, T-Shift sales) |  | 4 | Service |  | 78
FALSE | Take Declare Table & Declare things from office to event | Figure out what is needed to take for the Declare table, and load it up ahead of time to take to the event. |  | 4 | Service |  | 79
FALSE | Send thank you/ update email to pastors following the event | Send brief email with stats, highlights, and praises, thanking the pastors and leader for their partnership |  | Post | Follow Up |  | 80
FALSE | Go through budget to ensure all invoices and donations are final | Make sure everything look finalize on your end. Reach out to Business Admin to see if he sees any discrepancies, and possibly set a meeting to go through the budget. |  | Post | Follow Up |  | 81
FALSE | Submit payment to photographer | Work with Business Admin to submit payment. |  | Post | Photo |  | 82